## Rehab Statistics
Property | Initial Budget | Adjusted Budget | COE | Project Start Date | Idle Time | Contract Budget | Actually Spent | Percent Over Initial Budget | Initial Budget $/Sqft | Percent Over | Project Completion Date | Total Project Days | Rehab $'s Spent / Week Construction | SQFT | $/Sqft | Contractor | SOW Notes
Averages |  |  |  |  | 12.3333 | 44766.6667 | 54217 | 38.05% | 23.8171 | 20.12% |  | 48.1667 | 7930.2082 | 1750.1667 | 31.8855
Property 1 | 30000 | 33000 | 2012-01-01 | 2012-01-10 | 9 | 39000 | 50000 | 66.67% | 16.3934 | 28.21% | 2012-02-17 | 38 | 9210.5263 | 1830 | 27.3224 | Contractor A | full cosmetic rehab with half bath to full bath conversion (raised foundation)
Property 2 | 35000 | 40000 | 2012-01-17 | 2012-02-06 | 20 | 40500 | 43328 | 23.79% | 28.5714 | 6.983% | 2012-03-14 | 38 | 7981.4737 | 1225 | 35.3698 | Contractor B | Cosmetic interior and exterior rehab with reroof
Property 3 | 40000 | 40000 | 2012-04-27 | 2012-05-17 | 20 | 46600 | 47099 | 17.75% | 18.5701 | 1.071% | 2012-07-10 | 54 | 6105.4259 | 2154 | 21.8658 | Contractor C | Full cosmetic rehab interior and exterior
Property 4 | 55000 | 65000 | 2012-10-19 | 2012-10-29 | 10 | 65000 | 89000 | 61.82% | 20.9444 | 36.92% | 2013-01-04 | 68 | 9161.7647 | 2626 | 33.8919 | Contractor A | Full interior and exterior rehab, minor foundation issues, minor structural changes
Property 5 | 35000 | 38000 | 2012-12-27 | 2012-12-28 | 0 | 38500 | 52000 | 48.57% | 22.5806 | 35.06% | 2013-02-06 | 40 | 9100 | 1550 | 33.5484 | Contractor B | Full interior rehab with exterior paint inculding windows and ac
Property 6 | 40000 | 40000 | 2012-09-12 | 2012-09-27 | 15 | 39000 | 43875 | 9.688% | 35.8423 | 12.5% | 2012-11-16 | 51 | 6022.0588 | 1116 | 39.3145 | Contractor C | Major interior/exterior rehab, including demo of large unpermitted structure, able to keep flooring and kitchen cabs

## Contractor Statistics
Contractor A | Average Total Score | 5.5 | Tear | 3
Project | Contract Price | Actual Price | Difference | Score | Contract Completion Date | Actual Completion Date | Difference | Score | Total Project Time | Rehab $/ Week | Score | Punch List Given | Punch List Complete | Total Time | Score | BRR Give | BRR Complete | Total Time | Score | Average Score
Property 1 | 33000 | 40000 | 21.21% | 1 | 2012-01-31 | 2012-02-17 | 17 | 6 | 38 | 7368.4211 | 8 | 2012-02-17 | 2012-02-23 | 6 | 1 | 2012-03-10 | 2013-03-15 | 5 | 7 | 4.6
Property 2 | 60000 | 74000 | 23.33% | 1 | 2012-12-15 | 2013-01-04 | 20 | 5 | 68 | 7617.6471 | 8 | 2013-01-04 | 2013-01-06 | 2 | 9 | 2013-01-20 | 2013-01-22 | 2 | 9 | 6.4
Averages |  |  | #DIV/0! |  |  |  |  | 5.5 | 53 | 7493.0341 | 8 |  |  | 4 | 5 |  |  | 3.5 |  | 5.5
Contractor B | Average Total Score | 7.3 | Tear | 1
Project | Contract Price | Actual Price | Difference | Score | Contract Completion Date | Actual Completion Date | Difference | Score | Total Project Time | Rehab $/ Week | Score | Punch List Given | Punch List Complete | Total Time | Score | BRR Give | BRR Complete | Total Time | Score | Average Score
Property 1 | 33000 | 38000 | 15.15% | 6 | 2012-02-28 | 2012-03-08 | 8 | 8 | 38 | 7000 | 7 | 2013-03-14 | 2013-03-18 | 4 | 7 | 2013-04-05 | 2013-04-07 | 2 | 9 | 7.4
Property 2 | 38000 | 45000 | 18.42% | 5 | 2013-01-31 | 2013-02-06 | 6 | 9 | 40 | 7875 | 8 | 2013-02-06 | 2013-02-11 | 5 | 6 | 2013-02-28 | 2013-03-03 | 3 | 8 | 7.2
Averages |  |  | #DIV/0! |  |  |  |  | 8.5 | 39 | 7437.5 | 7.5 |  |  | 4.5 | 6.5 |  |  | 2.5 |  | 7.3
Contractor C | Average Total Score | 6.3 | Tear | 2
Project | Contract Price | Actual Price | Difference | Score | Contract Completion Date | Actual Completion Date | Difference | Score | Total Project Time | Rehab $/ Week | Score | Punch List Given | Punch List Complete | Total Time | Score | BRR Give | BRR Complete | Total Time | Score | Average Score
Property 1 | 41000 | 43000 | 4.878% | 10 | 2012-06-15 | 2012-07-10 | 25 | 5 | 54 | 5574.0741 | 1 | 2012-07-10 | 2012-07-13 | 3 | 9 | 2012-08-01 | 2012-08-02 | 1 | 10 | 7
Property 2 | 35000 | 39000 | 11.43% | 7 | 2012-10-31 | 2012-11-16 | 16 | 6 | 51 | 5352.9412 | 1 | 2012-11-17 | 2012-11-22 | 5 | 6 | 2012-12-10 | 2012-12-13 | 3 | 8 | 5.6
Averages |  |  | #DIV/0! |  |  |  |  | 5.5 | 52.5 | 5463.5076 | 1 |  |  | 4 | 7.5 |  |  | 2 |  | 6.3

## Scoring Breakdown
Contract price difference | under budget = 15 | 0-5% = 10 points | 6%-8% = 9 | 8%-10% = 8 | 11%-13% = 7 | 14-16% = 6 | 17%-19% = 5 | 20% + = 1
Contract completion difference | negative days = 15 | 0-3 days = 10 | 4-6 days = 9 | 7-10 days = 8 | 11-15 days = 7 | 16-20 days = 6 | 21-25 days = 5 | 26 days + = 1
Punch list total time | no punch list = 15 | 24 hours = 10 | 48 hours = 9 | 3 days = 8 | 4 days = 7 | 5 days = 6 | 6 + days = 1
BRR total time | 24 hours = 10 | 48 hours = 9 | 72 hours = 8 | 4 - 6 days = 7 | 7-9 days = 6 | 10 + days = 1
Rehab $/ Week Score | $10,001 + = 15 | $9,001 - $10,000 = 10 | $8,001 - $9,000 = 9 | $7,001 - $8,000 = 8 | $6,001 - $7,000 = 7 | Under $6,000 = 1